45-Day CRM Development Sprint Plan

Production-Ready SaaS CRM MVP

Project Overview

| Total Duration | 45 Days |
| --- | --- |
| Daily Hours | 12 Hours/Day |
| Total Hours | 540 Hours |
| Estimated Modules | 90–100 Modules |

Daily Working Schedule

| Time | Activity |
| --- | --- |
| 9:00–10:00 | Sprint Planning & Previous Day Review |
| 10:00–1:00 | Backend Development |
| 1:00–2:00 | Lunch |
| 2:00–5:00 | Frontend Development |
| 5:00–7:00 | API Integration |
| 7:00–8:00 | Dinner |
| 8:00–10:00 | QA + Bug Fix + Git Push + Documentation |

STAGE 1: FOUNDATION (Day 1–10)

Day 1: Project Initialization

UI/UX

☐ Requirement Analysis

☐ User Journey

☐ Feature Prioritization

Backend

☐ Create Repository

☐ Folder Structure

☐ Clean Architecture

☐ Environment Setup

☐ Docker

☐ RDB

☐ Logger

☐ Error Handler

Frontend

☐ Next.js Setup

☐ Tailwind

☐ ESLint

☐ Prettier

☐ Folder Structure

☐ Theme Provider

QA

☐ Project Checklist

☐ Test Plan

Deliverable: Production-ready project foundation.

Day 2: Database Design

Backend

☐ ER Diagram

☐ Collections

☐ Relationships

☐ Indexing

☐ Soft Delete

☐ Audit Fields

Frontend

☐ Layout

☐ Sidebar

☐ Header

☐ Breadcrumb

UI

☐ Dashboard Wireframe

☐ Navigation

QA

☐ Database Review

Day 3: Authentication

Backend

☐ JWT

☐ Refresh Token

☐ Login

☐ Register

☐ Forgot Password

☐ Reset Password

☐ Email Verification

☐ Session

☐ Middleware

Frontend

☐ Login Page

☐ Register Page

☐ Forgot Password

☐ Protected Routes

☐ Authentication Context

QA

☐ Authentication Testing

Day 4: User Management

☐ User CRUD

☐ Roles

☐ Permissions

☐ Teams

☐ Invite Users

☐ User Profile

☐ Change Password

☐ Activity Logs

Day 5: Dashboard APIs & UI

☐ Dashboard APIs

☐ Dashboard Cards

☐ Statistics

☐ Charts

☐ Sidebar Permission

☐ Responsive Dashboard

Day 6: Role-Based Access Control (RBAC)

☐ Permission Matrix

☐ Module Permission

☐ Action Permission

☐ Field Permission

☐ API Guard

Day 7: Notification & Audit System

☐ Notification Service

☐ Audit Logs

☐ System Logs

☐ Activity History

Day 8: Email & Background Jobs

☐ SMTP

☐ Email Service

☐ SMS Structure

☐ Queue

☐ Redis

☐ Background Jobs

Day 9: Global Search & Data Utilities

☐ Global Search

☐ Pagination

☐ Sorting

☐ Filtering

☐ Validation

☐ Response Standardization

Day 10: Foundation Review & Release v0.1

☐ Foundation Review

☐ Bug Fix

☐ Optimization

☐ Documentation

☐ Git Release v0.1

STAGE 2: SALES CRM (Day 11–23)

Day 11: Lead Database Setup

☐ Lead Database

☐ Lead CRUD API

☐ Validation

☐ Swagger

Day 12: Lead Frontend UI

☐ Lead Table

☐ Lead Form

☐ Search

☐ Filter

☐ Pagination

Day 13: Lead Kanban Board

☐ Drag Drop

☐ Status Change

☐ Bulk Update

Day 14: Lead Import & Export

☐ CSV Import

☐ Excel Import

☐ Export

☐ Duplicate Check

Day 15: Contacts Module

☐ CRUD

☐ Merge

☐ Import

☐ Export

Day 16: Companies Module

☐ CRUD

☐ Company Details

☐ Relationship

Day 17: Deals Module

☐ CRUD

☐ Deal Pipeline

☐ Probability

Day 18: Deal Pipeline Visualization

☐ Pipeline

☐ Forecast

☐ Closed Won

☐ Closed Lost

Day 19: Sales Analytics & Dashboard Integration

☐ Lead Analytics

☐ Sales Analytics

☐ Revenue

Day 20: Lead Conversion Flow

☐ Lead → Contact

☐ Lead → Company

☐ Lead → Deal

Day 21: Notes & Activity Timeline

☐ Notes

☐ Attachments

☐ Timeline

☐ Activity Log

Day 22: Bulk Operations

☐ Mass Update

☐ Mass Delete

☐ Mass Assign

Day 23: Sales CRM QA & Release v0.2

☐ Sales Regression Testing

☐ Performance Testing

☐ Bug Fixes

☐ Git Release v0.2

STAGE 3: PRODUCTIVITY (Day 24–35)

Day 24: Tasks Module

☐ CRUD

☐ Calendar

☐ Reminder

Day 25: Calls & Meetings

☐ Calls

☐ Meetings

☐ Timeline

Day 26: Notes & Comments

☐ Notes

☐ Comments

☐ Mentions

☐ Attachments

Day 27: Calendar Features

☐ Week View

☐ Month View

☐ Agenda

Day 28: Notifications

☐ Realtime Socket

☐ Toast Notifications

☐ Email Notification

Day 29: Internal Chat

☐ Message Thread

☐ Attachments

Day 30: Document Request System

☐ Upload

☐ Approval

☐ Versioning

Day 31: E-Signature Integration

☐ Document Status

☐ Audit Trail

Day 32: Support Ticket Module

☐ Priority

☐ Assignment

Day 33: Client Portal

☐ Portal Login

☐ Portal Dashboard

Day 34: Resources & Knowledge Base

☐ Knowledge Base

☐ FAQ

Day 35: Productivity QA & Release v0.3

☐ Bug Fix

☐ Optimization

☐ Git Release v0.3

STAGE 4: ADVANCED MODULES (Day 36–45)

Day 36: Reports Module

☐ Report Builder

☐ Export PDF

☐ Export Excel

Day 37: Analytics Dashboard

☐ Charts

☐ KPIs

☐ Revenue Analytics

Day 38: Campaign Management

☐ Email Campaign

☐ SMS Campaign

Day 39: Quotation & Invoice

☐ Quotation

☐ Estimate

☐ Invoice

☐ Payment

Day 40: Workflow Builder

☐ Automation

☐ Triggers

☐ Conditions

Day 41: System Settings

☐ SMTP

☐ Company Settings

☐ Roles & Permissions

☐ Backup

☐ Restore

Day 42: Performance Optimization

☐ Caching

☐ Lazy Loading

☐ Compression

Day 43: Security Audit

☐ OWASP Review

☐ Rate Limiting

☐ Input Validation

☐ Penetration Testing

Day 44: Full Regression & Deployment

☐ Full Regression Testing

☐ Bug Fix

☐ SSL Setup

☐ Monitoring Setup

Day 45: Final Delivery

☐ Production Deployment

☐ Smoke Testing

☐ UAT Fixes

☐ Final Documentation

☐ API Documentation

☐ Admin Manual

☐ User Manual

☐ Database Backup

☐ Git Tag (v1.0)

☐ Client Handover

Daily Definition of Done (DoD)

Every day must end with these mandatory checkpoints:

☐ Backend feature completed

☐ Frontend integrated with API

☐ UI reviewed against design

☐ Unit tests passed

☐ QA smoke testing completed

☐ Bugs fixed

☐ Code reviewed

☐ Swagger/API documentation updated

☐ Database migration verified

☐ Git branch merged

☐ Code pushed to GitHub

☐ Staging deployment successful

☐ Daily work log updated

☐ Next day's sprint planned

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

This workflow is structured as an enterprise-level Agile plan with approximately 540 working hours, suitable for delivering a production-quality SaaS CRM MVP within the 45-day target.